# Hedge Fund Roadmap – Phase 1 (April–June)

Partner Execution Plan

Date Generated: May 01, 2025

This document outlines the Phase 1 execution roadmap for building our hedge fund with the goal of surpassing top firms like Jane Street. The focus for this quarter is on disciplined execution, capital growth from ₹35,000 to ₹1,00,000, and launching the first version of our key trading infrastructure tools.

## Week 1–2 (Now till May 11)

- Deploy Trader Console v1 on Streamlit Cloud

- Log every Nifty trade with strict R-multiples (₹1500 risk, ₹3000–4500 reward)

- End-of-day trade review: execution score + reason for missed trades

- Daily capital update

- Begin building habit of reviewing data post-market (10 mins daily)

Objective: Lock execution discipline for 7 days straight.

## Week 3–4 (May 12–25)

- Launch Trade Analyst - Intraday Boost v1 (NSE F&O 225 filtering by 15-min R-factor vs 20-day avg)

- Output top 10 candidates for the day (with volatility/range tags)

- Start using filtered stocks to guide index entries

- Add equity curve chart in Trader Console

- Add execution score tracker graph

Objective: Trade Analyst generates real signals; Console tracks growth.

## Week 5–6 (May 26–June 8)

- Reach ₹1L target capital (start trading stock options)

- Expand Trade Analyst: add Option Apex (OI & IV shift scanner)

- Log 3–5 stock option trades (focus on directional + breakout moves)

- Start maintaining “Alpha Journal” of winning setups

Objective: Start building stock option watchlist using our tools.

## Week 7–8 (June 9–22)

- Design Trade Analyst v1.0 layout (3 modules: Intraday, Swing, Option)

- Add multi-page layout to Trader Console

- Risk layer: max drawdown warning + daily risk stop

- Review 30 days of trade logs: win %, score avg, R-multiple trends

Objective: Build confidence in tools and review edge systematically.

## Week 9–10 (June 23–July 1)

- Reach 100 logged trades milestone

- Summarize Q1 P&L and Execution Report

- Final polish on Trade Analyst before Phase 2 (Automation Phase)

- Prep GitHub + team structure for next phase scaling

Objective: Launch-ready tools and evaluated trading performance.